GREENEARTHX

GEX Twelve Gates

What each gate does, and why it exists in the GEX orchestration layer

Projects don’t become bankable because the story is convincing. They become bankable when the evidence converges.

A guide for client teams onboarded to GEX: project directors, engineering, commercial, legal, finance and treasury.

Bankability rules version 4.1.0 · October 2026

Contents

1. Why the gates exist

2. How a gate works in GEX

3. Document stages

4. The path from idea to operation

5. What GEX checks beyond documents

6. The twelve gates

G0 · Site Rights & Social License

G1 · Power, Utilities & Technology Basis

G2 · Green Certification Pathway

G3 · Feedstock & Logistics Terms

G4 · Binding Offtake

G5 · EPC Risk Priced

G6 · Independent Engineer Sign-off

G7 · Insurability Confirmed

G8 · Audit-Grade Financial Model

G9 · Permits Granted & Appeal Risk Managed

G10 · Financial Close

G11 · COD & Stabilization

7. Who does what

8. Getting started

# 1. Why the gates exist

Financing an e-fuel plant involves many parties: your own team, engineers, the EPC contractor, suppliers, buyers, insurers, certification bodies, permitting authorities, an independent engineer, and one or more lenders or investors. Each of them needs to know the same thing: which risks are closed, and which are still open.

Without a shared system, that knowledge is scattered across emails, data rooms and consultants’ reports. Every party keeps its own view of how ready the project is, and those views drift apart. Questions come one at a time, months apart, and the same document is requested again and again.

GEX is the digital layer that orchestrates this work. It keeps one record of your project’s evidence, applies one set of rules to it, and gives every party the same status. The twelve gates are the checkpoints of that layer. Each gate turns a milestone financiers care about into a defined list of evidence that GEX can check.

|  | Without an orchestration layer | With GEX |
| --- | --- | --- |
| Where evidence lives | Emails, data rooms and consultants’ folders | One project record. Each document is attached to the gate item it proves. |
| How ready the project is | Each party’s own judgement | One status, computed by the same rules for everyone |
| What a document is worth | Whatever its file name says | Its stage is declared and checked. A letter of intent cannot fill a signed-contract slot. |
| Who confirmed it | Lost in correspondence | An independent reviewer appointed to your project, never you and never GEX. The reviewer and every change are recorded |
| What financing is possible | Argued case by case | Each status names the financing decision it makes possible |

# 2. How a gate works in GEX

Every gate works the same way. You will see this cycle on the Gates & Evidence screen.

- You submit evidence. Each gate lists the documents it needs. Your team uploads each one against its item and records the document’s stage (see section 3).

- An independent reviewer verifies it. A reviewer appointed to your project for that gate confirms the document is authentic and is what it says it is, and names the document it verified. The reviewer is never your organisation and never GEX (section 7). A reviewer can lower the stage you declared, never raise it. Every change of status or stage is recorded.

- GEX re-evaluates the project. After every change, GEX recalculates every gate. Only verified documents at or above the required stage count.

- Each gate gets a result. Satisfied (every applicable item is in at its stage, the commitment level is met and no check fails), Blocked (a deal-breaker is missing, a coherence check fails or a trigger is active), Incomplete (other items are missing), or Waived (not required for your financing model).

- Your project moves up the ladder. Satisfied gates move the project to the next status. The ladder is strictly in order: no status can be skipped.

- Financing decisions become possible. Each gate names the financing decision it makes possible. If evidence is withdrawn or rejected, the project moves back down and GEX names the gate responsible.

Items that do not apply to you are removed Some items depend on how your plant gets its power: grid-connected, off-grid (behind-the-meter) or hybrid. GEX uses the configuration recorded for your project and leaves out the items that do not apply, so they never count against you. Some items protect an external lender and are asked only of a project-financed project. G6 and G8 consist only of such items, so they are waived whole when you fund from your own balance sheet. Every other gate, including the offtake (G4), insurance (G7) and the investment decision (G10), applies to every project. A waived gate counts towards your status but is never shown as satisfied by evidence.

# 3. Document stages

A document can be authentic and still not be enough. A genuine letter of intent is not a signed contract. That is why GEX records two things for every contract, permit, policy or opinion: whether it is verified, and how far it has progressed. Studies and analyses have no stage: they are either done or not.

| Stage | In GEX | What it means |
| --- | --- | --- |
| Intent | INTENT | A plan, mandate, letter of intent, MOU, or an application still in preparation |
| Term sheet | INDICATIVE | A term sheet, quotation or indication of terms, or an application submitted |
| Agreed form | AGREED | All terms settled, not yet signed or granted |
| Signed / granted | EXECUTED | Signed, bound, granted, issued or passed |
| In force | EFFECTIVE | In effect: conditions precedent satisfied, policy started, appeal period expired |

Each gate states the minimum stage it accepts. Early gates accept term sheets, because that is what can exist at that point. Financial Close requires everything signed. If you do not declare a stage for a contract or permit, it does not count until you do.

# 4. The path from idea to operation

The twelve gates lead your project up a ladder of statuses, from Speculative (an idea; nothing can be committed yet) to Operational. Each status is reached only when the gates before it are satisfied and, where shown, the offtake and the EPC have reached the level the status needs (section 5).

| Status | Gates that lead to it | Financing it makes possible |
| --- | --- | --- |
| Technically plausible | G0 Site Rights & Social License G1 Power, Utilities & Technology Basis | Grants and technical assistance; Seed, venture and angel investment |
| Commercially plausible | G2 Green Certification Pathway G3 Feedstock & Logistics Terms Offtake terms (O2 or better) for at least 60% of planned output | Strategic equity |
| Buildable | G4 Binding Offtake G5 EPC Risk Priced Offtake O4 · EPC E4 | Project equity |
| Structurally bankable | G6 Independent Engineer Sign-off G7 Insurability Confirmed Under project finance: offtake O6 | Development-finance, mezzanine and guarantee support (project finance) |
| Credit approved | G8 Audit-Grade Financial Model | A senior debt credit approval, conditional until financial close (project finance) |
| Financeable | G9 Permits Granted & Appeal Risk Managed G10 Financial Close Offtake in force: O7 (project finance) or O5 (balance sheet) · EPC E6 | Drawdown of the debt (project finance) |
| Operational | G11 COD & Stabilization | Refinancing through bonds or infrastructure funds |

# 5. What GEX checks beyond documents

A verified document is not the whole story. Two commitments are misread more than any other, the offtake and the EPC contract, so GEX grades each on a ladder. It works the level out from your verified documents and from the terms you record on five commitment cards: offtake, EPC, schedule, supply and model. You never type a level in.

| Offtake | What it means |
| --- | --- |
| O0 | No verified offtake document with a declared maturity. |
| O1 | MoU or letter of intent: a buyer exists; nothing binds. |
| O2 | Term sheet, heads of agreement or agreed form: commercial fit, not binding. |
| O3 | Signed, but not a binding commitment: a framework, volume or price not firm, or conditions with no longstop. |
| O4 | Binding, subject to conditions precedent with a longstop date. |
| O5 | Binding and effective: conditions satisfied; obligations run from COD. |
| O6 | Firm take-or-pay or take-if-tendered from an investment-grade or credit-supported buyer. |
| O7 | Project-finance grade: O6 plus tenor covering debt, assignment, step-in, a termination payment and allocated change in law. |

G4 needs O4. Commercially plausible needs offtake terms (O2 or better) for at least 60% of your planned output, the bar the EU Hydrogen Bank sets at application. Under project finance, Structurally bankable needs O6, and Financeable needs the offtake in force at O7; on a balance sheet, in force at O5.

| EPC | What it means |
| --- | --- |
| E0 | No contracting strategy and no verified EPC document. |
| E1 | Strategy defined: contracting model chosen, contractor candidates identified. |
| E2 | FEED complete (AACE Class 3 or better). |
| E3 | Priced proposal: a verified quotation or term sheet on the FEED basis. |
| E4 | Agreed form: price, schedule, guarantees, damages and caps, security and licence guarantee all agreed. |
| E5 | Executed; long-lead items ordered. |
| E6 | Effective and bankable: notice to proceed issued, security posted. |

G5 needs E4. Financeable needs E6.

Ten coherence checks. Commitments can each be sound and still contradict one another. GEX compares what the cards record: a first delivery date before guaranteed completion, contracted volume above guaranteed capacity, an offtake specification the EPC or licensor does not guarantee, delay exposure the EPC damages do not back, a longstop too short for permits and construction, feedstock or power contracted for less than the offtake, certification rules the power or CO2 sourcing cannot meet, force majeure defined differently across contracts, or model inputs that differ from the contracts. A failed check blocks its gate. A check with missing data shows as data missing: it never blocks and never counts as a pass.

Three triggers keep gates live after the investment decision: a power contract or public support terms revoked (blocks G1), certification suspended (G2 and G11), or the EPC contractor or a key OEM insolvent (G5).

# 6. The twelve gates

For each gate: what it does, why it exists, who in your organisation is accountable, who confirms it, what it makes possible, and the evidence it asks for.

Priority: Deal-breaker items block the gate on their own. Important and Advisory items must also be in for the gate to be satisfied. Minimum stage is shown for contracts, permits, policies and opinions; a dash means a study or analysis.

## G0 · Site Rights & Social License

Achievement gate   ·   leads to Technically plausible   ·   shown in GEX to Producer, Executive

| What it does | Confirms that you control the land the plant needs, that local zoning allows it, that the site suits the process, and that you know who in the community is affected. |
| --- | --- |
| Why it exists | Nothing else in a project is worth paying for if the site can be lost. Lenders will not fund a plant on land the project does not control. GEX puts this gate first so that no one, on your side or the financiers’, spends time on a project that cannot legally be built where it is planned. |
| Accountable | Project Director. Supported by: Legal counsel, land agent. |
| Confirmed by | An independent engineer, a lenders’ adviser, or the grant body’s own assessor |
| Makes possible | Grants and technical assistance |

What you provide

| Evidence | Prepared by | Minimum stage | Priority |
| --- | --- | --- | --- |
| Land Option or Lease Executed | Legal | Signed / granted | Deal-breaker |
| Zoning Compatibility Memo | Legal | — | Important |
| Stakeholder Map v1 | Project team | — | Advisory |
| Site Technical Suitability (major-hazard siting, geotechnics, logistics access) | Engineering | — | Important |

## G1 · Power, Utilities & Technology Basis

Readiness gate   ·   leads to Technically plausible   ·   shown in GEX to Producer

| What it does | Confirms that electricity, water and other critical utilities can reach the plant at the capacity and on the date your plan assumes, and that the conversion technology is proven enough for the scale you plan. |
| --- | --- |
| Why it exists | For an electrolysis-based plant, power is not one cost among many. It sets how much you produce, what it costs, its carbon intensity and whether it can be certified green. A plan built on power that cannot arrive in time has no business case. GEX shows only the items that fit your power configuration (grid-connected, off-grid or hybrid), so you are never asked for evidence that does not apply. The status this gate leads to is called Technically plausible, so it also asks for the technology itself: its maturity, its licensor, and a mass and energy balance that holds against your power profile. |
| Accountable | Head of Engineering. Supported by: Grid and utilities, power procurement, legal (water). |
| Confirmed by | An independent engineer, or the seed investor’s own adviser |
| Makes possible | Seed, venture and angel investment |

Term sheet now, signature later This is a readiness gate. A PPA at term-sheet stage is enough here. The signed PPA is required at Financial Close (G10).

What you provide

| Evidence | Prepared by | Minimum stage | Priority |
| --- | --- | --- | --- |
| Grid Interconnection Study (grid-connected and hybrid only) | Engineering | — | Deal-breaker |
| Grid Queue Position / Capacity Reservation (grid-connected and hybrid only) | Engineering | — | Important |
| Grid Connection Cost & Reinforcement Scope (grid-connected and hybrid only) | Engineering | — | Important |
| Connection Date vs COD Compatibility Memo (grid-connected and hybrid only) | Engineering | — | Important |
| PPA Register (counterparty, MW, €/MWh, tenor) (grid-connected and hybrid only) | Commercial | — | Important |
| Signed PPA / Term Sheet / LOI Evidence (grid-connected and hybrid only) | Commercial | Term sheet | Important |
| PPA Volume vs Plant Load Coverage Analysis (grid-connected and hybrid only) | Engineering | — | Important |
| PPA Tenor vs Debt / Offtake Tenor Comparison (grid-connected and hybrid only) | Finance | — | Advisory |
| Curtailment Assessment (grid node congestion + load profile) | Engineering | — | Important |
| Dispatch / Load Factor Impact on Production Volume | Engineering | — | Important |
| Water Source Plan (volume, cost, seasonal availability) | Engineering | — | Deal-breaker |
| Water Permit / Abstraction / Discharge Pathway | Legal | — | Important |
| BTM Generation Asset Spec & CAPEX (off-grid and hybrid only) | Engineering | — | Deal-breaker |
| Generation Yield Study (P50/P90) (off-grid and hybrid only) | Engineering | — | Important |
| Grid-Independence Design Note (off-grid and hybrid only) | Engineering | — | Important |
| Backup / Construction Power Plan (off-grid and hybrid only) | Project team | — | Important |
| Technology Maturity Dossier (readiness level, reference plants, operating hours, scale-up factor) | Engineering | — | Deal-breaker |
| Technology Licensor Identified — Term Sheet | Engineering | Term sheet | Important |
| Integrated Mass & Energy Balance at Design Basis (incl. hydrogen buffer and turndown vs power profile) | Engineering | — | Important |

## G2 · Green Certification Pathway

Readiness gate   ·   leads to Commercially plausible   ·   shown in GEX to Regulator, Offtaker

| What it does | Confirms that a named certification scheme applies to your project and that you can meet its rules, above all additionality and the timing and location of your renewable power, and that the product can be qualified to its specification standard. |
| --- | --- |
| Why it exists | The green premium, subsidies and many offtake prices depend on certification (RFNBO under RED III, 45V, ISCC). If the product fails the scheme’s rules it is not green in law, and the revenue case changes with it. This gate tests the pathway to the certificate, not the certificate itself, early enough to fix the design. |
| Accountable | Sustainability / Regulatory Lead. Supported by: Engineering, power procurement. |
| Confirmed by | Accredited certification body — never the producer |
| Makes possible | No financing on its own. Needed, with the other gates of its status, to reach Commercially plausible. |

Pathway now, certificate later This is a readiness gate: it confirms the pathway is feasible. Certification itself follows once the plant operates.

What you provide

| Evidence | Prepared by | Minimum stage | Priority |
| --- | --- | --- | --- |
| Certification Scheme Selected (RFNBO / RED III / 45V / ISCC) | Legal | — | Deal-breaker |
| Additionality Evidence (generator age, no state aid) | Engineering | — | Deal-breaker |
| Temporal & Geographic Correlation Alignment | Engineering | — | Important |
| GHG Methodology Memo | Engineering | — | Important |
| MRV Plan v1 (monitoring, reporting, verification) | Engineering | — | Important |
| Product Qualification Pathway (spec standard and annex status, e.g. ASTM D7566, ISO 6583) | Engineering | — | Important |

## G3 · Feedstock & Logistics Terms

Readiness gate   ·   leads to Commercially plausible   ·   shown in GEX to Producer

| What it does | Confirms that a named supplier has put feedstock terms on paper (volume, quality and duration), matched to your design basis and the certification scheme, and that transport and storage are planned. |
| --- | --- |
| Why it exists | Your production case assumes inputs arrive in the right quantity and quality for years. Financiers want to see that a real counterparty has committed to those terms, not only that supply is available in principle. |
| Accountable | Commercial / Procurement Lead. Supported by: Supply chain, engineering. |
| Confirmed by | An independent engineer, or the strategic investor’s own adviser |
| Makes possible | Strategic equity |

Term sheet now, signature later This is a readiness gate. A supply term sheet is enough here. The signed supply agreement is required at Financial Close (G10).

What you provide

| Evidence | Prepared by | Minimum stage | Priority |
| --- | --- | --- | --- |
| Feedstock Supply Terms (volume, quality, tenor) | Project team | Term sheet | Deal-breaker |
| Transport & Logistics Study | Engineering | — | Important |
| Storage Plan | Engineering | — | Important |
| Feedstock Specification & Eligibility Matched to Design Basis and Certification Scheme | Engineering | — | Important |

## G4 · Binding Offtake

Achievement gate   ·   leads to Buildable   ·   shown in GEX to Finance, Offtaker

| What it does | Confirms that a creditworthy buyer is contractually bound to take your product at a price that supports the debt, with the clauses lenders need, and that you can deliver what you sell. |
| --- | --- |
| Why it exists | Lenders lend against contracted revenue. The offtake contract is the most important document in most financings. A letter of intent or a term sheet does not pass this gate. A contract that binds the buyer does, even if it is still subject to conditions precedent with a realistic longstop date (offtake level O4, section 5). Assignment to lenders, step-in rights and a debt-sized termination payment are asked only under project finance. |
| Accountable | Chief Commercial Officer. Supported by: Sales, legal, treasury. |
| Confirmed by | The lenders’ adviser |
| Makes possible | Project equity |

What you provide

| Evidence | Prepared by | Minimum stage | Priority |
| --- | --- | --- | --- |
| Executed Offtake Agreement | Commercial | Signed / granted | Deal-breaker |
| Offtaker Credit Assessment | Finance | — | Deal-breaker |
| Credit Support (parent guarantee / letter of credit) (project finance only) | Finance | Signed / granted | Important |
| Take-or-Pay Floor (project finance only) | Legal | — | Important |
| Termination Payment Formula (project finance only) | Legal | — | Important |
| Assignment to Lenders (project finance only) | Legal | — | Important |
| Lender Step-in Rights (project finance only) | Legal | — | Important |
| Hedgeable Pricing Index (project finance only) | Finance | — | Important |
| Price Review / Reopener Mechanism | Legal | — | Important |
| Seller-Side Offtake Terms Reviewed (delivery, specification, delay and shortfall caps, certification warranty, longstop) | Legal | — | Important |

## G5 · EPC Risk Priced

Achievement gate   ·   leads to Buildable   ·   shown in GEX to Producer, Executive, Offtaker

| What it does | Confirms that the construction contract’s price, schedule and performance guarantees are settled in agreed form, so capital cost is a commitment rather than an estimate. |
| --- | --- |
| Why it exists | Cost overruns and delays are the most common reason projects fail. Lenders need to know who carries that risk and at what price before they commit. Agreed form, with fixed price or capped GMP and liquidated damages, is the point at which the number in your model can be relied on. GEX grades the EPC on a ladder (section 5) and this gate needs E4: FEED complete to AACE Class 3 or better, the licence and process guarantee agreed, the security package and damage caps agreed, and an independent technical review of the FEED. |
| Accountable | Project Director. Supported by: Engineering, legal, procurement. |
| Confirmed by | The independent engineer |
| Makes possible | No financing on its own. Needed, with the other gates of its status, to reach Buildable. |

Agreed form now, signature later The contract must be in agreed form here. It must be signed, with notice to proceed issued and security posted (E6), to reach Financeable.

What you provide

| Evidence | Prepared by | Minimum stage | Priority |
| --- | --- | --- | --- |
| EPC Contract — Fixed Price or Capped GMP (agreed form) | Project team | Agreed form | Deal-breaker |
| Delay & Performance Liquidated Damages | Legal | — | Deal-breaker |
| Date-Certain Construction Schedule | Project team | — | Important |
| Performance Test Protocol | Engineering | — | Important |
| Interface Matrix (EPC / OEM / balance of plant) | Engineering | — | Important |
| OEM Warranties (agreed form) | Engineering | Agreed form | Important |
| EPC Contractor Due Diligence | Project team | — | Important |
| FEED Complete — AACE Class 3 or Better | Engineering | — | Deal-breaker |
| Technology Licence & Process Performance Guarantee (or equivalent wrap) | Engineering | Agreed form | Important |
| Long-Lead Items Reserved | Project team | Agreed form | Important |
| EPC Security Package & Damage Caps (performance bond, parent guarantee, retention) | Legal | Agreed form | Important |
| Independent Technical Review of FEED | Independent engineer | — | Important |

## G6 · Independent Engineer Sign-off

Achievement gate   ·   leads to Structurally bankable   ·   shown in GEX to Finance, Regulator   ·   project finance only

| What it does | Confirms that the Independent Engineer has issued a final report on the technical basis of the project: energy balance, capital cost, operating cost and completion tests. |
| --- | --- |
| Why it exists | Lenders do not rely on the sponsor’s own technical case. They rely on an engineer they appoint. A draft report or an appointment letter does not pass; the final, issued report does. Your team supplies the data; the conclusion is the Independent Engineer’s. When you fund from your own balance sheet this gate is waived; the independent technical review of your FEED sits in G5 for every project. |
| Accountable | Lender (appoints and instructs). Supported by: Project team supplies data only. |
| Confirmed by | The independent engineer |
| Makes possible | Development-finance, mezzanine and guarantee support |

What you provide

| Evidence | Prepared by | Minimum stage | Priority |
| --- | --- | --- | --- |
| Independent Engineer Report — Issued (final) | Independent engineer | Signed / granted | Deal-breaker |
| Energy Balance Verified by the IE | Independent engineer | — | Deal-breaker |
| IE Opinion — CAPEX Reasonableness | Independent engineer | — | Important |
| IE Opinion — OPEX Reasonableness | Independent engineer | — | Important |
| Completion Test Definitions (IE-agreed) | Independent engineer | — | Important |

## G7 · Insurability Confirmed

Readiness gate   ·   leads to Structurally bankable   ·   shown in GEX to Finance

| What it does | Confirms that insurers have quoted your construction and operating insurance on terms the project, and its lenders where it is project-financed, can accept. |
| --- | --- |
| Why it exists | Lenders must know that the risks they cannot carry can be insured, and at what cost. Appointing a broker proves nothing about that; quotes from insurers do. First-of-a-kind exclusions can leave technology failure uninsured, so they are reviewed here, with any backstop for the OEM’s warranty. |
| Accountable | CFO / Treasury. Supported by: Broker, legal. |
| Confirmed by | The insurer, or the lenders’ adviser |
| Makes possible | No financing on its own. Needed, with the other gates of its status, to reach Structurally bankable. |

Quotes now, policies bound later This is a readiness gate. Quoted terms are enough here. The policies must be bound, with lenders named as loss payee, at Financial Close (G10).

What you provide

| Evidence | Prepared by | Minimum stage | Priority |
| --- | --- | --- | --- |
| Insurance Programme Terms — Quoted by Insurers | Treasury | Term sheet | Deal-breaker |
| Broker Market Report | Treasury | — | Important |
| Deductible Levels Accepted by Lenders (project finance only) | Treasury | — | Important |
| Exclusions Register Reviewed | Legal | — | Important |
| First-of-a-Kind Exclusions & OEM Warranty Backstop Reviewed | Treasury | — | Important |

## G8 · Audit-Grade Financial Model

Achievement gate   ·   leads to Credit approved   ·   shown in GEX to Finance   ·   project finance only

| What it does | Confirms that the financial model used for the lending decision is locked, audited by an independent model auditor, and shows downside cases and covenants. |
| --- | --- |
| Why it exists | A credit committee decides on a model. If the model is unaudited or still changing, the decision rests on numbers nobody has checked. This gate makes the project eligible for a lender’s credit decision; an approval stays conditional until financial close. |
| Accountable | CFO. Supported by: Financial modelling team. |
| Confirmed by | The lenders’ adviser, on the independent model auditor’s opinion |
| Makes possible | A senior debt credit approval, conditional until financial close |

What you provide

| Evidence | Prepared by | Minimum stage | Priority |
| --- | --- | --- | --- |
| Locked Base-Case Financial Model | Finance | — | Deal-breaker |
| Model Audit Opinion — Issued | Finance | Signed / granted | Deal-breaker |
| Lender Downside Cases | Finance | — | Important |
| Covenant Suite Defined | Finance | — | Important |
| DSRA & Maintenance Reserve Logic | Finance | — | Important |
| Hedging Plan (rates, FX, power) | Treasury | — | Important |
| Model Consistent with IE Findings | Finance | — | Important |

## G9 · Permits Granted & Appeal Risk Managed

Achievement gate   ·   leads to Financeable   ·   shown in GEX to Producer, Regulator, Offtaker

| What it does | Confirms that the environmental and construction permits are granted, that appeal risk has a legal opinion, and that the operating permit has a clear path. |
| --- | --- |
| Why it exists | A project cannot be built without its permits, and a successful appeal can stop construction after money is spent. Applications do not pass this gate; granted permits do. |
| Accountable | Regulatory / Permitting Lead. Supported by: Environmental consultant, legal. |
| Confirmed by | The lenders’ adviser, against the authority’s own decision |
| Makes possible | No financing on its own. Needed, with the other gates of its status, to reach Financeable. |

What you provide

| Evidence | Prepared by | Minimum stage | Priority |
| --- | --- | --- | --- |
| EIA / Environmental Permit — Granted | Legal | Signed / granted | Deal-breaker |
| Construction Permit — Granted | Legal | Signed / granted | Deal-breaker |
| Ancillary Permits — Granted | Legal | Signed / granted | Important |
| Legal Opinion on Appeal Risk | Legal | Signed / granted | Important |
| Operating Permit Pathway | Legal | — | Important |
| Stakeholder Management Plan v2 | Project team | — | Important |

## G10 · Financial Close

Achievement gate   ·   leads to Financeable   ·   shown in GEX to Finance, Offtaker

| What it does | Confirms the investment decision: every major contract signed and in force, funding committed, an O&M contract or operating organisation in place and insurance bound. Under project finance it also confirms the lenders’ conditions: conditions precedent satisfied, reserves funded, security perfected and legal opinions issued. |
| --- | --- |
| Why it exists | This is where terms become commitments. Everything that was allowed at term-sheet or agreed-form stage in earlier gates (PPA, feedstock, EPC, insurance) must now be signed and in force. Only then can the debt be drawn. |
| Accountable | CFO. Supported by: Legal, treasury, lender counsel. |
| Confirmed by | The lenders’ adviser (lender counsel confirms the conditions precedent) |
| Makes possible | Drawdown of the debt (project finance) |

What you provide

| Evidence | Prepared by | Minimum stage | Priority |
| --- | --- | --- | --- |
| Conditions Precedent Satisfied (project finance only) | Legal | In force | Deal-breaker |
| Funding Committed (equity injected, or board-approved funding) | Finance | Signed / granted | Deal-breaker |
| Debt Service Reserve Funded (project finance only) | Treasury | Signed / granted | Important |
| Security Package Perfected (project finance only) | Legal | In force | Deal-breaker |
| Insurance Bound & Certificates Delivered (lenders as loss payee where project-financed) | Treasury | In force | Important |
| All Major Project Contracts Executed (PPA, feedstock, EPC, O&M, offtake) | Legal | Signed / granted | Deal-breaker |
| Legal Opinions — Issued (project finance only) | Legal | Signed / granted | Deal-breaker |
| O&M Contract or Operating Organisation in Place | Project team | Signed / granted | Important |

## G11 · COD & Stabilization

Achievement gate   ·   leads to Operational   ·   shown in GEX to Producer, Executive, Offtaker

| What it does | Confirms that the plant has reached commercial operation, passed its performance tests, holds its operating permit, reports its carbon, has run stably for 6 to 12 months, has its first certificates issued, and has had its first on-specification deliveries accepted by the buyer. |
| --- | --- |
| Why it exists | Financing was granted on a promise of performance. This gate shows the promise was kept. A stable operating record is what allows the project to refinance on cheaper, longer-term money. |
| Accountable | Project Director → Operations Director. Supported by: Commissioning team, EPC contractor. |
| Confirmed by | The independent engineer (performance tests) and the certification body (certificates) |
| Makes possible | Refinancing through bonds or infrastructure funds |

What you provide

| Evidence | Prepared by | Minimum stage | Priority |
| --- | --- | --- | --- |
| COD / Taking-Over Certificate | Engineering | Signed / granted | Deal-breaker |
| Performance Tests Passed | Engineering | Signed / granted | Deal-breaker |
| Operating Permit — In Force | Legal | In force | Deal-breaker |
| MRV Reporting Live | Engineering | — | Important |
| 6–12 Months Stable Operation | Engineering | — | Important |
| Certification Audit Passed & First Certificates / Proofs of Sustainability Issued | Engineering | Signed / granted | Deal-breaker |
| First On-Specification Deliveries Accepted by the Offtaker | Commercial | Signed / granted | Important |

# 7. Who does what

The gates only work if the roles stay separate. GEX is built around four of them.

| Party | Is responsible for | Never |
| --- | --- | --- |
| Your organisation | Producing the evidence, meeting the milestone, and declaring honestly what each document is | Verifies its own evidence |
| GEX | The rules (what counts, at what stage, with what priority), appointing reviewers on the instruction of the party whose decision relies on the gate, and the record of who asserted what and when | Owns your evidence, verifies it, or makes the financing decision |
| The independent reviewer | Confirming that the evidence is authentic and is what it claims to be, for the gates its role covers: a certifier (G2, G11), the independent engineer (G0, G1, G3, G5, G6, G11), the lenders’ adviser (G0, G4, G7 to G10), the insurer (G7), or the grant body’s or investor’s own reviewer (G0, G1, G3) | Belongs to your organisation or to GEX, or raises the stage you declared |
| The capital provider | The credit, investment, grant or drawdown decision | Treats a GEX gate as a substitute for its own approval |

What GEX does and does not do GEX shows when the evidence conditions for a financing decision are met. The bank, investor, development-finance institution or grant authority still makes that decision. The gates make the case complete and visible to everyone at the same time. They do not replace anyone’s judgement.

# 8. Getting started

- Check your power configuration. Make sure GEX records whether your plant is grid-connected, off-grid or hybrid, so the right G1 items appear.

- Ask for your reviewers early. Nothing counts until an independent reviewer is appointed to your project for its gates. GEX appoints reviewers on the instruction of your lender, grant body, investor or insurer, so ask them to instruct GEX as soon as they are engaged.

- Record your commitments on the cards. Enter the terms of your offtake, EPC, schedule, supply and model on the commitment cards. GEX derives the offtake and EPC levels from them and runs the coherence checks.

- Name an owner for every item. Each item shows the function that prepares it (Legal, Engineering, Commercial, Finance, Treasury). Decide which person in that function owns it.

- Start with G0 and G1. They are the first status on the ladder, and the other gates build on them.

- Clear deal-breakers first. A single missing deal-breaker blocks its gate, however complete the rest is.

- Declare stages honestly. Record a term sheet as a term sheet. It counts where a term sheet is enough, and a reviewer will lower an overstated stage anyway.

- Plan for Financial Close early. Every term sheet you file in G1, G3, G5 and G7 must be signed by G10. Knowing that from the start avoids a rush at the end.