# The GEX Process

How a green-fuel project becomes bankable on GreenEarthX: what is asked, who supplies it, who checks it, and what each step makes possible. For producers, offtakers, financiers, insurers, certifiers and verifiers.

Projects don't become bankable because the story is convincing. They become bankable when the evidence converges.

Generated from the running rules — evidence rules 4.2.0 · 12 gates · 93 evidence items · 31 maturity requirements · 9 states · 2026-10-28

# Who owns what

| PARTY | OWNS | NEVER OWNS |
| --- | --- | --- |
| The client (producer, and each party to its contracts) | The evidence, the milestones, the declaration of what each instrument is and how far it has progressed. | The verification of its own evidence. |
| The counterparty to a contract | Confirming, on the contract's token, the terms it agreed — which also verifies that contract. | Terms it has not confirmed. |
| The independent reviewer | The assertion that a study, opinion, audit or the producer's own plan is authentic and is what it claims to be. | A commercial interest in the outcome, and the power to raise a declared maturity. |
| GEX | The rule: what counts, at what maturity, with what severity; the scoring; and the record of who asserted what, and when. | The evidence, its verification, and the capital decision. |
| The capital provider | The grant, investment, credit or drawdown decision. | Letting a GEX gate stand in for its own approval. |

# The path of one evidence item

- Requested. Each item is assigned to a named person at the company that owns the work, with what it blocks.

- Submitted. The document is uploaded and its SHA-256 recorded; the submitter declares the instrument's maturity. A new document returns the item to submitted: what was verified was the earlier file.

- Verified. By someone independent of the submitter and of the project owner — the contract's counterparty for a contract, an appointed independent reviewer for everything else. Verification names the document on file.

- Scored. The engine counts an item only when it is verified at or above the maturity its gate requires.

- Judged. Each gate gets one answer (below); satisfied gates set the project's state.

- Made eligible. A state makes a capital decision eligible. The capital provider still decides.

# Maturity

Verification answers whether a document is authentic. Maturity answers how far the instrument behind it has progressed — a letter of intent can be perfectly authentic. The submitter declares maturity; a reviewer may confirm or lower it, never raise it. An instrument with no declared maturity does not count.

- INTENT — Plan, mandate, letter of intent, MOU, strategy, or application in preparation.

- INDICATIVE — Term sheet, quotation, indication of terms, or application submitted.

- AGREED — Agreed-form document with all terms settled, not yet signed or granted.

- EXECUTED — Signed, bound, granted, issued or passed.

- EFFECTIVE — In force: conditions precedent satisfied, policy incepted, appeal period expired.

# Who verifies

GEX verifies nothing. A contract is verified by its counterparty's confirmation on the contract's token; an independent reviewer may also take part, but is not required. Studies, analyses, opinions, audits and the producer's own plan need an independent reviewer, appointed by GEX staff on the instruction of a named party. Each reviewer role covers fixed gates:

| REVIEWER | GATES |
| --- | --- |
| Certifier | G2, G11 |
| Independent engineer | G0, G1, G3, G5, G6, G11 |
| Lenders' adviser | G0, G4, G7, G8, G9, G10 |
| Insurer | G7 |
| Grant assessor | G0 |
| Seed investor's adviser | G1 |
| Strategic investor's adviser | G3 |

Never the submitter or its company, and never the project owner's company.

# A gate's answer

SATISFIED
Every applicable item verified at its maturity, every required commitment reached, every cross-contract check passed.

BLOCKED
A deal-killer is missing, a commitment is below the level the gate needs, a cross-contract check failed, or an event undermines the gate.

UNRESOLVED
The items are verified, but a cross-contract check cannot run because confirmed terms are missing. Missing data is never a pass.

INCOMPLETE
Items are still to be verified.

WAIVED
Not required for this financing model. Counts toward the ladder; never shown as satisfied by evidence.

# Project premises

Two premises decide which evidence applies. The financing model: balance-sheet funding drops the items that only protect an external lender and waives the gates made only of them (G6, G8). The power model (grid-connected, off-grid behind the meter, hybrid): each drops the items that belong to the others.

A change that removes evidence takes effect only when its supporting document is registered and a second party confirms it — another party to the project (a funder, the counterparty) or GEX staff, never the company that proposed it. Any party may register a document contesting a premise; while it is contested the protective premise applies (project finance, every power item), until GEX staff decide. A change that adds evidence back applies at once.

# Contract terms and the contract token

Documents can each satisfy a gate and still contradict one another. So the terms that matter — volumes, tenors, dates, specifications, damages caps — are recorded once, and the engine compares them across contracts. Every contract has a token: an append-only, hash-chained record of its versions and confirmations. A change to the terms is a new version on the token. Only terms in the latest version confirmed by the other party reach the engine; until then the checks that need them read UNRESOLVED.

| CONTRACT | WHO CONFIRMS | ITS CONFIRMATION ALSO VERIFIES |
| --- | --- | --- |
| Offtake | The counterparty company registered on the contract | Executed Offtake Agreement, Credit Support (parent guarantee / letter of credit) |
| Power purchase | The counterparty company registered on the contract | Signed PPA / Term Sheet / LOI Evidence |
| Feedstock supply | The counterparty company registered on the contract | Feedstock Supply Terms (volume, quality, tenor) |
| EPC | The counterparty company registered on the contract | EPC Contract — Fixed Price or Capped GMP (agreed form), EPC Security Package & Damage Caps (performance bond, parent guarantee, retention) |
| Technology licence | The counterparty company registered on the contract | Technology Licensor Identified — Term Sheet, Technology Licence & Process Performance Guarantee (or equivalent wrap) |
| Technical basis and schedule | An independent reviewer appointed for G5 | — |
| Financial model | An independent reviewer appointed for G8 | — |

A reported adverse event — the contractor insolvent, power or support revoked, certification suspended — applies at once and blocks the gates it undermines; clearing it needs a confirmation.

| CHECK | WHAT IS COMPARED | GATE |
| --- | --- | --- |
| C1 | First delivery after guaranteed completion plus commissioning allowance | G4 |
| C2 | Contracted volume within guaranteed capacity × availability | G4 |
| C3 | Offtake specification guaranteed by the EPC or licensor | G4 |
| C4 | Offtake delay exposure backed by EPC damages, contingency and sponsor support | G5 |
| C5 | Longstop covers permits, investment decision, construction and commissioning | G4 |
| C6 | Feedstock and power contracted for the offtake's volume and tenor | G4 |
| C7 | Power and CO2 sourcing meet the certification the offtake requires | G4 |
| C8 | Producer certifies under the scheme the offtake requires | G4 |
| C9 | Force majeure aligned across offtake, EPC and supply contracts | G10 |
| C10 | Model inputs equal contract terms; offtake tenor covers debt | G8 |

Numeric equality allows 1 % for rounding in a model — not a margin for error. COMMERCIALLY PLAUSIBLE also needs offtake terms covering at least 60 % of planned output.

# The ladder

Nine states, strictly in order: no state is reachable without every gate of every state before it.

| STATE | WHAT MUST BE SATISFIED | CAPITAL DECISION MADE ELIGIBLE |
| --- | --- | --- |
| Speculative Idea stage — nothing can be committed yet | Entry state | — |
| Technically Plausible Site and technology basis confirmed | G0 Site Rights & Social License, G1 Power, Utilities & Technology Basis | Grants & TA, Seed / VC / Angel |
| Commercially Plausible Commercially defined — offtake term sheets cover most of the output | G2 Green Certification Pathway, G3 Feedstock & Logistics Terms | Strategic Equity |
| Buildable Commitment-ready — producer and offtaker can sign binding-with-conditions | G4 Binding Offtake, G5 EPC Risk Priced | Project Equity |
| Structurally Bankable Independently validated | G6 Independent Engineer Sign-off, G7 Insurability Confirmed | DFI / Mezz / Guarantees |
| Credit Approved Credit approved — conditional until financial close | G8 Audit-Grade Financial Model | Senior Debt Credit Approval (conditional) |
| Financeable Committed — investment decision taken | G9 Permits Granted & Appeal Risk Managed, G10 Financial Close | Debt Drawdown |
| Operational Delivering — certified product accepted by the buyer | G11 COD & Stabilization | Refinance / Bonds / Infra |
| Refinancing Eligible Proven — refinancing possible | No gate defined yet — this state cannot be reached | — |

# What moves a project backwards

- A verified item replaced by a new document, rejected, or withdrawn.

- A cross-contract check that fails, or a term change not yet confirmed.

- A counterparty or reviewer disputing terms it had confirmed.

- A premise contested or rejected.

- An adverse event: insolvency, revoked power or support, suspended certification.

Each names the gate responsible, and the capital eligibility it carried is withdrawn.

# Re-evaluation, reports and who sees what

Every change that can move a gate — evidence, a document, a premise, a contract term, a confirmation — re-evaluates the project at once. When the state or a gate's answer changes, the project's designated executives are notified; by default the owner's executives. Each project has a report showing its state, the share of evidence verified, and every open item side by side — evidence to verify, commitments not reached, contracts that disagree, data missing — each with its owner, due date and what it holds back.

Each party sees the gates that concern its role. The project's state and overall figure always cover every gate, and the screen says so when a viewer sees fewer.

# What GEX never does

- Verify a party's evidence, or confirm a party's terms.

- Commit, release or draw capital. A state makes a decision eligible; the capital provider decides.

- Let a gate stand in for a lender's, investor's or grant authority's own approval.

- Show a figure the engine did not compute from verified evidence.

# The twelve gates

Readiness gates test what can be true at their stage — indicative terms, a feasible pathway, confirmed insurability; every instrument they rely on must be executed at financial close. Achievement gates require the achievement itself.

## G0  Site Rights & Social License   Achievement gate

| LEADS TO | Technically Plausible |
| --- | --- |
| CAPITAL DECISION MADE ELIGIBLE | Grants & TA |
| VERIFIED BY | Independent engineer, Lenders' adviser, Grant assessor |
| SEEN BY | Producer, Executive and the owner's executives |

| EVIDENCE ITEM | SEVERITY | MATURITY | OWNER | APPLIES TO | VERIFIED BY |
| --- | --- | --- | --- | --- | --- |
| Land Option or Lease Executed | Deal-killer | EXECUTED | Legal | All | Independent reviewer |
| Zoning Compatibility Memo | Warning | — | Legal | All | Independent reviewer |
| Stakeholder Map v1 | Advisory | — | Project | All | Independent reviewer |
| Site Technical Suitability (major-hazard siting, geotechnics, logistics access) | Warning | — | Engineering | All | Independent reviewer |

## G1  Power, Utilities & Technology Basis   Readiness gate

| LEADS TO | Technically Plausible |
| --- | --- |
| CAPITAL DECISION MADE ELIGIBLE | Seed / VC / Angel |
| VERIFIED BY | Independent engineer, Seed investor's adviser |
| SEEN BY | Producer and the owner's executives |

| EVIDENCE ITEM | SEVERITY | MATURITY | OWNER | APPLIES TO | VERIFIED BY |
| --- | --- | --- | --- | --- | --- |
| Grid Interconnection Study | Deal-killer | — | Engineering | Grid Connected, Hybrid | Independent reviewer |
| Grid Queue Position / Capacity Reservation | Warning | — | Engineering | Grid Connected, Hybrid | Independent reviewer |
| Grid Connection Cost & Reinforcement Scope | Warning | — | Engineering | Grid Connected, Hybrid | Independent reviewer |
| Connection Date vs COD Compatibility Memo | Warning | — | Engineering | Grid Connected, Hybrid | Independent reviewer |
| PPA Register (counterparty, MW, €/MWh, tenor) | Warning | — | Sales | Grid Connected, Hybrid | Independent reviewer |
| Signed PPA / Term Sheet / LOI Evidence | Warning | INDICATIVE | Sales | Grid Connected, Hybrid | Counterparty (Power purchase) |
| PPA Volume vs Plant Load Coverage Analysis | Warning | — | Engineering | Grid Connected, Hybrid | Independent reviewer |
| PPA Tenor vs Debt / Offtake Tenor Comparison | Advisory | — | Finance | Grid Connected, Hybrid | Independent reviewer |
| Curtailment Assessment (grid node congestion + load profile) | Warning | — | Engineering | All | Independent reviewer |
| Dispatch / Load Factor Impact on Production Volume | Warning | — | Engineering | All | Independent reviewer |
| Water Source Plan (volume, cost, seasonal availability) | Deal-killer | — | Engineering | All | Independent reviewer |
| Water Permit / Abstraction / Discharge Pathway | Warning | — | Legal | All | Independent reviewer |
| BTM Generation Asset Spec & CAPEX | Deal-killer | — | Engineering | Off Grid Btm, Hybrid | Independent reviewer |
| Generation Yield Study (P50/P90) | Warning | — | Engineering | Off Grid Btm, Hybrid | Independent reviewer |
| Grid-Independence Design Note | Warning | — | Engineering | Off Grid Btm, Hybrid | Independent reviewer |
| Backup / Construction Power Plan | Warning | — | Project | Off Grid Btm, Hybrid | Independent reviewer |
| Technology Maturity Dossier (readiness level, reference plants, operating hours, scale-up factor) | Deal-killer | — | Engineering | All | Independent reviewer |
| Technology Licensor Identified — Term Sheet | Warning | INDICATIVE | Engineering | All | Counterparty (Technology licence) |
| Integrated Mass & Energy Balance at Design Basis (incl. hydrogen buffer and turndown vs power profile) | Warning | — | Engineering | All | Independent reviewer |

## G2  Green Certification Pathway   Readiness gate

| LEADS TO | Commercially Plausible |
| --- | --- |
| CAPITAL DECISION MADE ELIGIBLE | — |
| VERIFIED BY | Certifier |
| SEEN BY | Regulator, Offtaker and the owner's executives |

| EVIDENCE ITEM | SEVERITY | MATURITY | OWNER | APPLIES TO | VERIFIED BY |
| --- | --- | --- | --- | --- | --- |
| Certification Scheme Selected (RFNBO / RED III / 45V / ISCC) | Deal-killer | — | Legal | All | Independent reviewer |
| Additionality Evidence (generator age, no state aid) | Deal-killer | — | Engineering | All | Independent reviewer |
| Temporal & Geographic Correlation Alignment | Warning | — | Engineering | All | Independent reviewer |
| GHG Methodology Memo | Warning | — | Engineering | All | Independent reviewer |
| MRV Plan v1 (monitoring, reporting, verification) | Warning | — | Engineering | All | Independent reviewer |
| Product Qualification Pathway (spec standard and annex status, e.g. ASTM D7566, ISO 6583) | Warning | — | Engineering | All | Independent reviewer |

## G3  Feedstock & Logistics Terms   Readiness gate

| LEADS TO | Commercially Plausible |
| --- | --- |
| CAPITAL DECISION MADE ELIGIBLE | Strategic Equity |
| VERIFIED BY | Independent engineer, Strategic investor's adviser |
| SEEN BY | Producer and the owner's executives |

| EVIDENCE ITEM | SEVERITY | MATURITY | OWNER | APPLIES TO | VERIFIED BY |
| --- | --- | --- | --- | --- | --- |
| Feedstock Supply Terms (volume, quality, tenor) | Deal-killer | INDICATIVE | Project | All | Counterparty (Feedstock supply) |
| Transport & Logistics Study | Warning | — | Engineering | All | Independent reviewer |
| Storage Plan | Warning | — | Engineering | All | Independent reviewer |
| Feedstock Specification & Eligibility Matched to Design Basis and Certification Scheme | Warning | — | Engineering | All | Independent reviewer |

## G4  Binding Offtake   Achievement gate

| LEADS TO | Buildable |
| --- | --- |
| CAPITAL DECISION MADE ELIGIBLE | Project Equity |
| VERIFIED BY | Lenders' adviser |
| SEEN BY | Finance, Offtaker and the owner's executives |

Also needs the offtake commitment at level O4 or above.

Cross-contract checks on this gate: C1 First delivery after guaranteed completion plus commissioning allowance; C2 Contracted volume within guaranteed capacity × availability; C3 Offtake specification guaranteed by the EPC or licensor; C5 Longstop covers permits, investment decision, construction and commissioning; C6 Feedstock and power contracted for the offtake's volume and tenor; C7 Power and CO2 sourcing meet the certification the offtake requires; C8 Producer certifies under the scheme the offtake requires.

| EVIDENCE ITEM | SEVERITY | MATURITY | OWNER | APPLIES TO | VERIFIED BY |
| --- | --- | --- | --- | --- | --- |
| Executed Offtake Agreement | Deal-killer | EXECUTED | Sales | All | Counterparty (Offtake) |
| Offtaker Credit Assessment | Deal-killer | — | Finance | All | Independent reviewer |
| Credit Support (parent guarantee / letter of credit) | Warning | EXECUTED | Finance | All | Counterparty (Offtake) |
| Take-or-Pay Floor | Warning | — | Legal | All | Independent reviewer |
| Termination Payment Formula | Warning | — | Legal | All | Independent reviewer |
| Assignment to Lenders | Warning | — | Legal | All | Independent reviewer |
| Lender Step-in Rights | Warning | — | Legal | All | Independent reviewer |
| Hedgeable Pricing Index | Warning | — | Finance | All | Independent reviewer |
| Price Review / Reopener Mechanism | Warning | — | Legal | All | Independent reviewer |
| Seller-Side Offtake Terms Reviewed (delivery, specification, delay and shortfall caps, certification warranty, longstop) | Warning | — | Legal | All | Independent reviewer |

## G5  EPC Risk Priced   Achievement gate

| LEADS TO | Buildable |
| --- | --- |
| CAPITAL DECISION MADE ELIGIBLE | — |
| VERIFIED BY | Independent engineer |
| SEEN BY | Producer, Executive, Offtaker and the owner's executives |

Also needs the epc commitment at level E4 or above.

Cross-contract checks on this gate: C4 Offtake delay exposure backed by EPC damages, contingency and sponsor support.

| EVIDENCE ITEM | SEVERITY | MATURITY | OWNER | APPLIES TO | VERIFIED BY |
| --- | --- | --- | --- | --- | --- |
| EPC Contract — Fixed Price or Capped GMP (agreed form) | Deal-killer | AGREED | Project | All | Counterparty (EPC) |
| Delay & Performance Liquidated Damages | Deal-killer | — | Legal | All | Independent reviewer |
| Date-Certain Construction Schedule | Warning | — | Project | All | Independent reviewer |
| Performance Test Protocol | Warning | — | Engineering | All | Independent reviewer |
| Interface Matrix (EPC / OEM / balance of plant) | Warning | — | Engineering | All | Independent reviewer |
| OEM Warranties (agreed form) | Warning | AGREED | Engineering | All | Independent reviewer |
| EPC Contractor Due Diligence | Warning | — | Project | All | Independent reviewer |
| FEED Complete — AACE Class 3 or Better | Deal-killer | — | Engineering | All | Independent reviewer |
| Technology Licence & Process Performance Guarantee (or equivalent wrap) | Warning | AGREED | Engineering | All | Counterparty (Technology licence) |
| Long-Lead Items Reserved | Warning | AGREED | Project | All | Independent reviewer |
| EPC Security Package & Damage Caps (performance bond, parent guarantee, retention) | Warning | AGREED | Legal | All | Counterparty (EPC) |
| Independent Technical Review of FEED | Warning | — | Independent Engineer | All | Independent reviewer |

## G6  Independent Engineer Sign-off   Achievement gate

| LEADS TO | Structurally Bankable |
| --- | --- |
| CAPITAL DECISION MADE ELIGIBLE | DFI / Mezz / Guarantees |
| VERIFIED BY | Independent engineer |
| SEEN BY | Finance, Regulator and the owner's executives |

Every item protects a lender: waived for a balance-sheet-funded project.

| EVIDENCE ITEM | SEVERITY | MATURITY | OWNER | APPLIES TO | VERIFIED BY |
| --- | --- | --- | --- | --- | --- |
| Independent Engineer Report — Issued (final) | Deal-killer | EXECUTED | Independent Engineer | All | Independent reviewer |
| Energy Balance Verified by the IE | Deal-killer | — | Independent Engineer | All | Independent reviewer |
| IE Opinion — CAPEX Reasonableness | Warning | — | Independent Engineer | All | Independent reviewer |
| IE Opinion — OPEX Reasonableness | Warning | — | Independent Engineer | All | Independent reviewer |
| Completion Test Definitions (IE-agreed) | Warning | — | Independent Engineer | All | Independent reviewer |

## G7  Insurability Confirmed   Readiness gate

| LEADS TO | Structurally Bankable |
| --- | --- |
| CAPITAL DECISION MADE ELIGIBLE | — |
| VERIFIED BY | Lenders' adviser, Insurer |
| SEEN BY | Finance and the owner's executives |

| EVIDENCE ITEM | SEVERITY | MATURITY | OWNER | APPLIES TO | VERIFIED BY |
| --- | --- | --- | --- | --- | --- |
| Insurance Programme Terms — Quoted by Insurers | Deal-killer | INDICATIVE | Treasury | All | Independent reviewer |
| Broker Market Report | Warning | — | Treasury | All | Independent reviewer |
| Deductible Levels Accepted by Lenders | Warning | — | Treasury | All | Independent reviewer |
| Exclusions Register Reviewed | Warning | — | Legal | All | Independent reviewer |
| First-of-a-Kind Exclusions & OEM Warranty Backstop Reviewed | Warning | — | Treasury | All | Independent reviewer |

## G8  Audit-Grade Financial Model   Achievement gate

| LEADS TO | Credit Approved |
| --- | --- |
| CAPITAL DECISION MADE ELIGIBLE | Senior Debt Credit Approval (conditional) |
| VERIFIED BY | Lenders' adviser |
| SEEN BY | Finance and the owner's executives |

Every item protects a lender: waived for a balance-sheet-funded project.

Cross-contract checks on this gate: C10 Model inputs equal contract terms; offtake tenor covers debt.

| EVIDENCE ITEM | SEVERITY | MATURITY | OWNER | APPLIES TO | VERIFIED BY |
| --- | --- | --- | --- | --- | --- |
| Locked Base-Case Financial Model | Deal-killer | — | Finance | All | Independent reviewer |
| Model Audit Opinion — Issued | Deal-killer | EXECUTED | Finance | All | Independent reviewer |
| Lender Downside Cases | Warning | — | Finance | All | Independent reviewer |
| Covenant Suite Defined | Warning | — | Finance | All | Independent reviewer |
| DSRA & Maintenance Reserve Logic | Warning | — | Finance | All | Independent reviewer |
| Hedging Plan (rates, FX, power) | Warning | — | Treasury | All | Independent reviewer |
| Model Consistent with IE Findings | Warning | — | Finance | All | Independent reviewer |

## G9  Permits Granted & Appeal Risk Managed   Achievement gate

| LEADS TO | Financeable |
| --- | --- |
| CAPITAL DECISION MADE ELIGIBLE | — |
| VERIFIED BY | Lenders' adviser |
| SEEN BY | Producer, Regulator, Offtaker and the owner's executives |

| EVIDENCE ITEM | SEVERITY | MATURITY | OWNER | APPLIES TO | VERIFIED BY |
| --- | --- | --- | --- | --- | --- |
| EIA / Environmental Permit — Granted | Deal-killer | EXECUTED | Legal | All | Independent reviewer |
| Construction Permit — Granted | Deal-killer | EXECUTED | Legal | All | Independent reviewer |
| Ancillary Permits — Granted | Warning | EXECUTED | Legal | All | Independent reviewer |
| Legal Opinion on Appeal Risk | Warning | EXECUTED | Legal | All | Independent reviewer |
| Operating Permit Pathway | Warning | — | Legal | All | Independent reviewer |
| Stakeholder Management Plan v2 | Warning | — | Project | All | Independent reviewer |

## G10  Financial Close   Achievement gate

| LEADS TO | Financeable |
| --- | --- |
| CAPITAL DECISION MADE ELIGIBLE | Debt Drawdown |
| VERIFIED BY | Lenders' adviser |
| SEEN BY | Finance, Offtaker and the owner's executives |

Cross-contract checks on this gate: C9 Force majeure aligned across offtake, EPC and supply contracts.

| EVIDENCE ITEM | SEVERITY | MATURITY | OWNER | APPLIES TO | VERIFIED BY |
| --- | --- | --- | --- | --- | --- |
| Conditions Precedent Satisfied | Deal-killer | EFFECTIVE | Legal | All | Independent reviewer |
| Funding Committed (equity injected, or board-approved funding) | Deal-killer | EXECUTED | Finance | All | Independent reviewer |
| Debt Service Reserve Funded | Warning | EXECUTED | Treasury | All | Independent reviewer |
| Security Package Perfected | Deal-killer | EFFECTIVE | Legal | All | Independent reviewer |
| Insurance Bound & Certificates Delivered (lenders as loss payee where project-financed) | Warning | EFFECTIVE | Treasury | All | Independent reviewer |
| All Major Project Contracts Executed (PPA, feedstock, EPC, O&M, offtake) | Deal-killer | EXECUTED | Legal | All | Independent reviewer |
| Legal Opinions — Issued | Deal-killer | EXECUTED | Legal | All | Independent reviewer |
| O&M Contract or Operating Organisation in Place | Warning | EXECUTED | Project | All | Independent reviewer |

## G11  COD & Stabilization   Achievement gate

| LEADS TO | Operational |
| --- | --- |
| CAPITAL DECISION MADE ELIGIBLE | Refinance / Bonds / Infra |
| VERIFIED BY | Certifier, Independent engineer |
| SEEN BY | Producer, Executive, Offtaker and the owner's executives |

| EVIDENCE ITEM | SEVERITY | MATURITY | OWNER | APPLIES TO | VERIFIED BY |
| --- | --- | --- | --- | --- | --- |
| COD / Taking-Over Certificate | Deal-killer | EXECUTED | Engineering | All | Independent reviewer |
| Performance Tests Passed | Deal-killer | EXECUTED | Engineering | All | Independent reviewer |
| Operating Permit — In Force | Deal-killer | EFFECTIVE | Legal | All | Independent reviewer |
| MRV Reporting Live | Warning | — | Engineering | All | Independent reviewer |
| 6–12 Months Stable Operation | Warning | — | Engineering | All | Independent reviewer |
| Certification Audit Passed & First Certificates / Proofs of Sustainability Issued | Deal-killer | EXECUTED | Engineering | All | Independent reviewer |
| First On-Specification Deliveries Accepted by the Offtaker | Warning | EXECUTED | Sales | All | Independent reviewer |

Generated from pf_engine evidence rules 4.2.0, app.core.abac and app.core.contract_tokens on 2026-10-28 by backend/scripts/export_gex_process.py.